## Video Production Mgmt Timeline
VIDEO PRODUCTION MANAGEMENT TIMELINE
| PROJECT NAME | [5 empty] | START DATE
AllY fix our content day
| PROJECT MANAGER |  | ACADEMIC COMNTACT |  |  |  | END DATE
| Lachlan |  | Jaimee
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
| Gather assets from Fran | Complete | Lachlan | 2024-01-02 | 2024-01-04 | 2 | Jaimee to send images of BB AllY graphics to create | Not Started
| Start work on intro/outro cards | In Progress | Lachlan | 2024-01-04 | 2024-01-11 | 7 |  | In Progress
| Create 30 second edit | In Progress | Lachlan | 2024-01-07 | 2024-01-11 | 4 |  | Complete
| Send to Fran for review | Not Started | Lachlan | 2024-01-10 | 2024-01-15 | 5 |  | On Hold
| Make any changes | Not Started | Lachlan | 2024-01-13 | 2024-01-20 | 7
| Send final version to Fran | Not Started | Lachlan | 2024-01-16 | 2024-01-22 | 6
0
0
0
0
0
0
0
0
0
0

## BLANK Video Prod Mgmt Timeline
VIDEO PRODUCTION MANAGEMENT TIMELINE
| PROJECT NAME | [5 empty] | START DATE
| PROJECT MANAGER |  | ACADEMIC CONTACT |  |  |  | END DATE
AT RISK | TASK | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS | STATUS
[6 empty] | 0 |  | Not Started
[6 empty] | 0 |  | In Progress
[6 empty] | 0 |  | Complete
[6 empty] | 0 |  | On Hold
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Double-click Horizontal (Value) Axis to format Bound Minimum and Bound Maximum settings under Axis Options.* Delete any unpopulated rows in your table.*